## Sheet1
Scenario No. | Module name | Scenario Description | Requirement ID | Cond. No. | Condition Description | Action No. | Action | Priority | Expected Result | Actual Result in Test Iteration 1 | Date | Status | Expected Result | Actual Result in Test Iteration 2 | Date | Status | Remarks
1 |  | Search by city |  | 0 | Check by count | 1 |  | Low | 50 | AssertionError: expected 32 equal to 50 | 2018-07-06 | Fail | 32 | 32 | 2018-07-06 | Pass
2 |  | Search by city and name |  | 0 | Check by count | 2 |  | Low | 7 | AssertionError: expected 2 equal to 7 | 2018-07-06 | Fail | 2 | 2 | 2018-07-06 | Pass
3 |  | Search by name |  | 0 | Check by datatype | 3 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
4 |  | Search by city and name |  | 0 | Check by value | 4 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
5 |  | Search by city and rating |  | 0 | Check by count | 5 |  | Low | 1900 | AssertionError: expected 1179 to 1900 | 2018-07-07 | Fail | 1179 | 1179 | 2018-07-07 | Pass
6 |  | Search by city and rating |  | 1 | Check value using sort | 6 |  | Low | Adhikari Group Of Hotels The Mall | AssertionError: expected Nirankari Group Of Hotels The Mall equal to Adhikari Group Of Hotels The Mall | 2018-07-06 | Fail | Nirankari Group Of Hotels The Mall | Nirankari Group Of Hotels The Mall | 2018-07-06 | Pass
7 |  | Search by city and rating |  | 1 | Check by datatype | 7 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
8 |  | Search by city and rating |  | 1 | Check by value | 8 |  | Low | Hotel Mountain Blue | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
9 |  | Search by city and rating |  | 1 | Check by value | 9 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
10 |  | Search by city |  | 1 | Check value using sort | 10 |  | Low | Treebo hotels Manali | AssertionError: expected Club Mahindra Manali equal to Club Mahindra Manali | 2018-07-07 | Fail | Club Mahindra Manali | Club Mahindra Manali | 2018-07-07 | Pass
11 |  | Seach by city and room count |  | 1 | Check by count | 11 |  | Low | 48 | AssertionError: expected 48 equal to 26 | 2018-07-06 | Fail | 26 | 26 | 2018-07-06 | Pass
12 |  | Seach by city and room type |  | 1 | Check by datatype | 12 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
13 |  | Seach by city and room value |  | 1 | Check by value | 13 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-06 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-06 | Pass
14 |  | Seach by name city and rating |  | 1 | Check by count | 14 |  | Low | 8 | AssertionError: expected 2 equal to 8 | 2018-07-07 | Fail | 2 | 2 | 2018-07-07 | Pass
15 |  | Search by name city and room count |  | 1 | Check by count | 15 |  | Low | 3 | AssertionError: expected 2 equal to 3 | 2018-07-07 | Fail | 2 | 2 | 2018-07-07 | Pass
16 |  | Search by name |  | 1 | Check by count | 16 |  | Low | 4 | AssertionError: expected 2 equal to 4 | 2018-07-06 | Fail | 4 | 4 | 2018-07-06 | Pass
17 |  | Search by name city and rating |  | 1 | Check by datatype | 17 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
18 |  | Search by name city and rating |  | 1 | Check by value | 18 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-06 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-06 | Pass
19 |  | Search by name and rating |  | 1 | Check by count | 19 |  | Low | 4 | AssertionError: expected 2 equal to 4 | 2018-07-07 | Fail | 2 | 2 | 2018-07-07 | Pass
20 |  | Search by name rating and room |  | 1 | Check by count | 20 |  | Low | 3 | AssertionError: expected 2 equal to 3 | 2018-07-07 | Fail | 2 | 2 | 2018-07-07 | Pass
21 |  | Search by name rating and room |  | 2 | Check by datatype | 21 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
22 |  | Search by name rating and room |  | 2 | Check by value | 22 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-06 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-06 | Pass
23 |  | Search by name and rating |  | 2 | Check by datatype | 23 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
24 |  | Search by name and rating |  | 2 | Check by value | 24 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
25 |  | Search by name |  | 2 | Check value using sort | 25 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
26 |  | Search by name room and city |  | 2 | Check by datatype | 26 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
27 |  | Search by name room and city |  | 2 | Check by value | 27 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-06 | Fail | hotel Mountain Face | Hotel Mountain Face | 2018-07-06 | Pass
28 |  | Search by name and room |  | 2 | Check by count | 28 |  | Low | 4 | AssertionError: expected 2 equal to 4 | 2018-07-06 | Fail | 2 | 2 | 2018-07-06 | Pass
29 |  | Search by name room rating and city |  | 2 | Check by datatype | 29 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-07 | Fail | string | string | 2018-07-07 | Pass
30 |  | Search by name room and city |  | 2 | Check by value | 30 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
31 |  | Search by name and room |  | 2 | Check by datatype | 31 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
32 |  | Search by name and room |  | 2 | Check by value | 32 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-06 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-06 | Pass
33 |  | Search by name |  | 2 | Check by datatype | 33 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
34 |  | Search by name |  | 2 | Check by value | 34 |  | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
35 |  | Search by rating |  | 2 | Check by count | 35 |  | Low | 670 | AssertionError: expected 484 equal to 484 | 2018-07-07 | Fail | 484 | 484 | 2018-07-07 | Pass
36 |  | Search by rating |  | 3 | Check value using sort | 36 |  | Low | OYO Rooms Dwarka | AssertionError: expected OYO Rooms Rohini equal to OYO Rooms Dwarka | 2018-07-06 | Fail | OYO Rooms Rohini | OYO Rooms Rohini | 2018-07-06 | Pass
37 |  | Search by rating and room |  | 3 | Check by count | 37 |  | Low | 2500 | AssertionError: expected 2149 equals to 2500 | 2018-07-06 | Fail | 2149 | 2149 | 2018-07-06 | Pass
38 |  | Search by rating and room |  | 3 | Check by datatype | 38 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-06 | Fail | string | string | 2018-07-06 | Pass
39 |  | Search by rating and room |  | 3 | Check by value | 39 |  | Low | Central hotel ooty | AssertionError: expected Global Village Ooty equals to Central hotel ooty | 2018-07-07 | Fail | Global Village Ooty | Global Village Ooty | 2018-07-07 | Pass
40 |  | Search by rating |  | 3 | Check by datatype | 40 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-07 | Fail | string | string | 2018-07-07 | Pass
41 |  | Search by rating |  | 3 | Check by value | 41 |  | Low | Central hotel ooty | AssertionError: expected Global Village Ooty equals to Central hotel ooty | 2018-07-07 | Fail | Global Village Ooty | Global Village Ooty | 2018-07-07 | Pass
42 |  | Search by room rating and city |  | 3 | Check by count | 42 |  | Low | 30 | AssertionError: expected 21 equals to 30 | 2018-07-07 | Fail | 21 | 21 | 2018-07-07 | Pass
43 |  | Search by room rating and city and name |  | 3 | Check by count | 43 |  | Low | 1 | AssertionError: expected 2 equals to 1 | 2018-07-07 | Fail | 2 | 2 | 2018-07-07 | Pass
44 |  | Search by room rating and city |  | 3 | Check by datatype | 44 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-07 | Fail | string | string | 2018-07-07 | Pass
45 |  | Search by room rating and city |  | 3 | Check by value | 45 | ` | Low | Hotel Mountain Blue | AssertionError: expected Hotel Mountain Face equal to Hotel Mountain Blue | 2018-07-07 | Fail | Hotel Mountain Face | Hotel Mountain Face | 2018-07-07 | Pass
46 |  | Search by room |  | 3 | Check value using sort | 46 |  | Low | Manjusha hotels | AssertionError: expected Mangrove suites equal to Manjusha hotels | 2018-07-07 | Fail | Mangrove suites | Mangrove suites | 2018-07-07 | Pass
47 |  | Search by room |  | 3 | Check by datatype | 47 |  | Low | number | AssertionError: expected 'string' equal to 'number' | 2018-07-07 | Fail | string | string | 2018-07-07 | Pass
48 |  | Search by room |  | 3 | Check by value | 48 |  | Low | Central hotel ooty | AssertionError: expected Global Village Ooty equals to Central hotel ooty | 2018-07-07 | Fail | Global Village Ooty | Global Village Ooty | 2018-07-07 | Pass
49 |  | Search by roomcount |  | 3 | Check by count | 49 |  | Low | 120 | AssertionError: expected 117 equals to 120 | 2018-07-07 | Fail | 117 | 117 | 2018-07-07 | Pass
50 |  | Search by city |  | 3 | Check by length | 50 |  | Low | 4 | AssertionError: expected 3 equals to 6 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
51 |  | Search by city name |  | 3 | Check by length | 51 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
52 |  | Search by city and rating |  | 3 | Check by length | 52 |  | Low | 4 | AssertionError: expected 3 equals to 7 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
53 |  | Search by city and room |  | 3 | Check by length | 53 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
54 |  | Search by name |  | 3 | Check by length | 54 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
55 |  | Search by name and rating |  | 3 | Check by length | 55 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
56 |  | Search by name and room |  | 3 | Check by length | 56 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
57 |  | Search by name room rating and city |  | 3 | Check by length | 57 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
58 |  | Search by rating |  | 3 | Check by length | 58 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
59 |  | Search by rating city and name |  | 3 | Check by length | 59 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
60 |  | Search by rating and room |  | 3 | Check by length | 60 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
61 |  | Search by room |  | 3 | Check by length | 61 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass
62 |  | Search by room rating and city |  | 3 | Check by length | 62 |  | Low | 4 | AssertionError: expected 3 equals to 4 | 2018-07-07 | Fail | 3 | 3 | 2018-07-07 | Pass